## Project Overview
E-COMMERCE WEBSITE - MANUAL TESTING PROJECT
Quality Assurance Document ¦ Prepared by: QA Team ¦ Version: 1.0
PROJECT INFORMATION | [5 empty] | TEST ENVIRONMENT
Project Name: | E-Commerce Website Manual Testing |  |  |  |  | Project Manager: | QA Lead
Version: | 1.0 |  |  |  |  | Test Manager: | Senior QA Engineer
Start Date: | 01-March-2025 |  |  |  |  | Environment: | Staging / UAT
End Date: | 31-March-2025 |  |  |  |  | Browser: | Chrome, Firefox, Edge, Safari
Status: | In Progress |  |  |  |  | OS: | Windows 10, macOS, Android, iOS
TESTING SCOPE
In Scope | User Registration & Login, Product Search & Browsing, Shopping Cart, Checkout & Payment, Order Management, User Profile, Admin Panel, Wishlist, Reviews & Ratings, Security Testing
Out of Scope | Performance Load Testing, API Automation Testing, Third-party payment gateway backend, Mobile App Native Testing
TEST MODULES SUMMARY
Module ID | Module Name | Total TCs | Pass | Fail | Blocked | Not Executed | Pass % | Priority | Status
M-01 | User Registration & Login | 20 | 18 | 1 | 0 | 1 | 90% | High | In Progress
M-02 | Product Search & Browsing | 18 | 15 | 2 | 0 | 1 | 83.33% | High | In Progress
M-03 | Shopping Cart | 15 | 13 | 1 | 1 | 0 | 86.67% | High | In Progress
M-04 | Checkout & Payment | 22 | 19 | 2 | 1 | 0 | 86.36% | Critical | In Progress
M-05 | Order Management | 14 | 12 | 1 | 0 | 1 | 85.71% | High | In Progress
M-06 | User Profile | 10 | 9 | 0 | 0 | 1 | 90% | Medium | In Progress
M-07 | Wishlist | 8 | 7 | 1 | 0 | 0 | 87.5% | Medium | Completed
M-08 | Product Reviews & Ratings | 10 | 8 | 1 | 1 | 0 | 80% | Medium | In Progress
M-09 | Admin Panel | 16 | 14 | 1 | 0 | 1 | 87.5% | High | In Progress
M-10 | Security Testing | 12 | 10 | 2 | 0 | 0 | 83.33% | Critical | In Progress
TOTAL | All Modules | 145 | 125 | 12 | 3 | 500% | 86.21%

## Login & Registration
🛒 E-COMMERCE WEBSITE - TEST CASES ¦ Login & Registration
TC ID | Module | Test Scenario | Test Case Description | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Priority | Remarks
TC-001 | Registration | Valid Registration | Verify user can register with valid details | User not registered | 1. Go to Register page 2. Enter valid name, email, password 3. Click Register | Name: John Doe Email: john@test.com Pass: Test@123 | User registered successfully, confirmation email sent | User registered and redirected to home | Pass | Critical
TC-002 | Registration | Duplicate Email | Verify error on duplicate email registration | Email already exists | 1. Go to Register 2. Enter existing email 3. Click Register | Email: existing@test.com | Error: Email already registered | Error message displayed | Pass | High
TC-003 | Registration | Invalid Email Format | Verify validation for invalid email | None | 1. Enter invalid email 2. Click Register | Email: john@ | Validation error shown | Validation error shown | Pass | High
TC-004 | Registration | Weak Password | Verify password strength validation | None | 1. Enter password less than 8 chars 2. Click Register | Pass: 1234 | Error: Password too weak | Error displayed | Pass | High
TC-005 | Registration | Empty Fields | Verify mandatory field validation | None | 1. Leave all fields blank 2. Click Register | All fields empty | Required field errors shown | All validations triggered | Pass | Medium
TC-006 | Login | Valid Login | Verify successful login with correct credentials | User registered | 1. Enter valid email & password 2. Click Login | Email: john@test.com Pass: Test@123 | User logged in and redirected to dashboard | Login successful | Pass | Critical
TC-007 | Login | Invalid Password | Verify error on wrong password | User registered | 1. Enter valid email 2. Enter wrong password 3. Click Login | Email: john@test.com Pass: Wrong123 | Error: Invalid credentials | Error message shown | Pass | Critical
TC-008 | Login | Unregistered Email | Verify error for unregistered email | None | 1. Enter unregistered email 2. Click Login | Email: notexist@test.com | Error: User not found | Error displayed | Pass | High
TC-009 | Login | Account Lockout | Verify account locks after 5 failed attempts | User registered | 1. Enter wrong password 5 times | Wrong password x5 | Account locked, lockout message shown | Account locked after 5 attempts | Pass | Critical
TC-010 | Login | Remember Me | Verify "Remember Me" functionality | User registered | 1. Check Remember Me 2. Login 3. Close browser 4. Reopen site | Valid credentials | User stays logged in | User session persists | Pass | Medium
TC-011 | Login | Forgot Password | Verify forgot password flow | User registered | 1. Click Forgot Password 2. Enter email 3. Check reset link | Email: john@test.com | Reset email sent | Reset email received | Pass | High
TC-012 | Login | Social Login - Google | Verify Google OAuth login | Google account available | 1. Click Login with Google 2. Select account | Google credentials | User logged in via Google | Google login works | Pass | Medium
TC-013 | Logout | Valid Logout | Verify user can logout successfully | User logged in | 1. Click Logout button | Logged in user | User logged out, redirected to home | Logout successful | Pass | High
TC-014 | Logout | Session Expiry | Verify session expires after timeout | User logged in | 1. Keep session idle for 30 mins | Idle session | Session expires, user redirected to login | Session expired correctly | Pass | High
TC-015 | Security | SQL Injection Login | Verify protection against SQL injection | None | 1. Enter SQL injection in email: ' OR '1'='1 | SQL injection string | Login rejected, no access granted | Attack blocked | Pass | Critical | Security test
TC-016 | Security | XSS in Registration | Verify XSS protection in registration form | None | 1. Enter <script>alert("xss")</script> in name field | XSS payload | Input sanitized, no script executed | XSS blocked | Fail | Critical | Bug reported: BUG-001
TC-017 | Password | Password Reset | Verify password reset with valid token | Reset email received | 1. Click reset link 2. Enter new password 3. Confirm | New pass: NewTest@123 | Password changed successfully | Password reset works | Pass | High
TC-018 | Password | Expired Reset Token | Verify expired reset token is rejected | Old reset link | 1. Click expired reset link | Expired token | Error: Link expired | Expired link rejected | Pass | Medium
TC-019 | Registration | Phone Number Validation | Verify phone number format validation | None | 1. Enter invalid phone 2. Submit | Phone: 123 | Validation error for phone format | Error shown | Pass | Low
TC-020 | Registration | Email Verification | Verify email verification link works | Register new user | 1. Register 2. Click verification link in email | New user email | Account verified, user can login | Email verified successfully | Pass | Critical

## Product & Search
E-COMMERCE WEBSITE - TEST CASES ¦ Product & Search
TC ID | Module | Test Scenario | Test Case Description | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Priority | Remarks
TC-021 | Search | Valid Product Search | Search for existing product by name | Products in DB | 1. Enter product name 2. Click Search | Query: "Nike Shoes" | Relevant products displayed | Products shown correctly | Pass | Critical
TC-022 | Search | No Results Search | Search for non-existent product | Products in DB | 1. Enter non-existent product 2. Click Search | Query: "xyzabc123" | "No products found" message shown | No results message shown | Pass | High
TC-023 | Search | Category Filter | Filter products by category | Products with categories | 1. Select category "Electronics" 2. Click Filter | Category: Electronics | Only electronics shown | Filter works correctly | Pass | High
TC-024 | Search | Price Range Filter | Filter by price range | Products with prices | 1. Set min $10, max $100 2. Apply | Price: $10-$100 | Products in price range shown | Price filter works | Pass | High
TC-025 | Search | Sort by Price Low-High | Sort products by price ascending | Products listed | 1. Select Sort: Price Low to High | Default product list | Products sorted lowest to highest price | Sorting correct | Pass | Medium
TC-026 | Search | Sort by Price High-Low | Sort products by price descending | Products listed | 1. Select Sort: Price High to Low | Default product list | Products sorted highest to lowest price | Sorting correct | Pass | Medium
TC-027 | Search | Sort by Rating | Sort products by customer rating | Products with ratings | 1. Select Sort: Top Rated | Products with ratings | Highest rated products shown first | Rating sort works | Pass | Medium
TC-028 | Product Detail | Product Page Load | Verify product detail page loads correctly | Products in DB | 1. Click on any product | Any product | All product info shown: name, price, images, description | Product page loads correctly | Pass | Critical
TC-029 | Product Detail | Product Images | Verify product images display and zoom | Product with multiple images | 1. Open product 2. Click image thumbnail 3. Hover for zoom | Product with gallery | Images display, thumbnails work, zoom on hover | Image gallery works | Pass | Medium
TC-030 | Product Detail | Out of Stock Display | Verify OOS products shown correctly | OOS product in DB | 1. Open OOS product | Out of stock product | Add to cart disabled, OOS label shown | OOS indicator works | Pass | High
TC-031 | Product Detail | Product Size Selection | Verify size selection functionality | Product with sizes | 1. Open product 2. Select size | Product: T-shirt | Selected size highlighted, stock updated | Size selection works | Pass | High
TC-032 | Browse | Category Navigation | Navigate through category menu | Categories in DB | 1. Hover over Categories 2. Select subcategory | Category menu | Correct subcategory products shown | Navigation works | Pass | High
TC-033 | Browse | Pagination | Verify pagination on product listing | Multiple pages of products | 1. Go to product list 2. Click page 2 | Product list page | Next page of products loads | Pagination works | Pass | Medium
TC-034 | Browse | Breadcrumb Navigation | Verify breadcrumb navigation works | Inside category | 1. Navigate to Electronics > Mobiles 2. Click breadcrumb link | Nested category | Correct page loads on breadcrumb click | Breadcrumb works | Pass | Low
TC-035 | Search | Search with Special Characters | Search with special characters | Products in DB | 1. Search: 'Nike@#$%' | Special char query | Results shown or "no results", no errors | Handled gracefully | Fail | Medium | Bug: App crashes on % char
TC-036 | Search | Brand Filter | Filter by brand | Multi-brand products | 1. Select Brand: Nike 2. Apply | Brand: Nike | Only Nike products shown | Brand filter works | Pass | High
TC-037 | Search | Color Filter | Filter by color | Products with colors | 1. Select Color: Red 2. Apply | Color: Red | Only red products shown | Color filter works | Pass | Medium
TC-038 | Product Detail | Product Description | Verify complete product info shown | Product with full info | 1. Open product page | Any product | All details: specs, description, features shown | All info displayed | Pass | High

## Shopping Cart
E-COMMERCE WEBSITE - TEST CASES ¦ Shopping Cart
TC ID | Module | Test Scenario | Test Case Description | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Priority | Remarks
TC-039 | Cart | Add to Cart | Verify product added to cart successfully | User logged in, product available | 1. Open product 2. Click "Add to Cart" | Any available product | Product added, cart count increases | Product added successfully | Pass | Critical
TC-040 | Cart | Cart Count Update | Verify cart counter updates | Empty cart | 1. Add 3 different products | Three products | Cart icon shows count "3" | Cart count is 3 | Pass | High
TC-041 | Cart | Increase Quantity | Verify quantity can be increased | Item in cart | 1. Click + button on item | Item qty: 1 | Quantity increases to 2, price updates | Quantity and price updated | Pass | High
TC-042 | Cart | Decrease Quantity | Verify quantity can be decreased | Item qty > 1 in cart | 1. Click - button on item | Item qty: 3 | Quantity decreases to 2, price updates | Quantity and price updated | Pass | High
TC-043 | Cart | Remove Item | Verify item can be removed from cart | Item in cart | 1. Click Remove/Delete on item | Item in cart | Item removed, cart updates | Item removed correctly | Pass | High
TC-044 | Cart | Empty Cart | Verify empty cart state | Remove all items | 1. Remove all items from cart | Items in cart | "Cart is empty" message with shopping link | Empty cart state shown | Pass | Medium
TC-045 | Cart | Cart Total Calculation | Verify cart total is calculated correctly | Multiple items in cart | 1. Add items 2. Check subtotal | Item1: $50, Item2: $30 | Total shows $80 + applicable tax | Total calculation correct | Pass | Critical
TC-046 | Cart | Max Quantity Limit | Verify max quantity limit per item | Item in cart | 1. Try to add more than stock | Stock qty: 5, try to add 10 | Warning: Cannot exceed available stock | Stock limit enforced | Pass | High
TC-047 | Cart | Apply Coupon Code | Verify valid coupon applies discount | Valid coupon available | 1. Enter coupon code 2. Click Apply | Coupon: SAVE10 | Discount applied, new total shown | Discount applied correctly | Pass | High
TC-048 | Cart | Invalid Coupon Code | Verify invalid coupon rejected | None | 1. Enter invalid coupon 2. Click Apply | Coupon: INVALID | Error: Invalid or expired coupon | Error message shown | Pass | Medium
TC-049 | Cart | Save Cart for Later | Verify cart persists after logout | Items in cart, logged in | 1. Add items to cart 2. Logout 3. Login again | User session | Cart items persist after re-login | Cart saved correctly | Pass | High
TC-050 | Cart | Guest Cart Merge | Verify guest cart merges on login | Item in guest cart | 1. Add item as guest 2. Login | Guest cart with item | Guest cart merged with user cart | Cart merge works | Fail | Medium | Bug reported: BUG-002
TC-051 | Cart | Price Change in Cart | Verify price updates if product price changes | Item in cart | 1. Add item 2. Admin updates price 3. Check cart | Price changed product | Cart shows updated price with notification | Price update reflected | Pass | High
TC-052 | Cart | OOS Item in Cart | Verify handling of OOS item in cart | Item in cart | 1. Add item 2. Item goes OOS 3. Check cart | OOS product | Warning shown, checkout blocked for OOS item | OOS warning displayed | Pass | High
TC-053 | Cart | Move to Wishlist | Verify item can be moved from cart to wishlist | Logged in user, item in cart | 1. Click "Move to Wishlist" on item | Cart item | Item moved to wishlist, removed from cart | Move to wishlist works | Pass | Medium

## Checkout & Payment
E-COMMERCE WEBSITE - TEST CASES ¦ Checkout & Payment
TC ID | Module | Test Scenario | Test Case Description | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Priority | Remarks
TC-054 | Checkout | Checkout Flow | Verify complete checkout process | Items in cart, user logged in | 1. Click Checkout 2. Enter address 3. Select shipping 4. Pay | Full checkout data | Order placed successfully, confirmation shown | Order placed | Pass | Critical
TC-055 | Checkout | Guest Checkout | Verify guest can checkout | Items in cart | 1. Checkout without login 2. Enter email 3. Complete order | Guest user | Order placed as guest, confirmation email sent | Guest checkout works | Pass | High
TC-056 | Address | Add Shipping Address | Verify shipping address can be added | Logged in user | 1. Go to checkout 2. Add new address | Full address data | Address saved and selectable | Address added correctly | Pass | Critical
TC-057 | Address | Invalid Address | Verify validation for incomplete address | Checkout page | 1. Submit with missing fields | Incomplete address | Validation errors for missing fields | Validation shown | Pass | High
TC-058 | Address | Edit Saved Address | Verify saved address can be edited | Saved address exists | 1. Click Edit on address 2. Update 3. Save | Updated address | Address updated successfully | Edit works | Pass | Medium
TC-059 | Shipping | Shipping Method Selection | Verify shipping options available | Address entered | 1. View shipping options | Delivery address | Multiple shipping options shown with prices/ETA | Shipping options shown | Pass | High
TC-060 | Shipping | Free Shipping Threshold | Verify free shipping on qualifying amount | Cart above threshold | 1. Add items above $50 2. Check shipping | Cart total: $75 | Free shipping option available | Free shipping unlocked | Pass | Medium
TC-061 | Payment | Credit Card Payment | Verify credit card payment works | Valid card available | 1. Enter card details 2. Click Pay | Card: 4111111111111111 | Payment processed, order confirmed | Payment successful | Pass | Critical
TC-062 | Payment | Invalid Card Number | Verify invalid card rejected | Checkout page | 1. Enter invalid card number 2. Click Pay | Card: 1234567890 | Error: Invalid card number | Validation shown | Pass | Critical
TC-063 | Payment | Expired Card | Verify expired card rejected | Checkout page | 1. Enter expired card 2. Click Pay | Expiry: 01/20 | Error: Card expired | Expired card rejected | Pass | Critical
TC-064 | Payment | PayPal Payment | Verify PayPal payment works | PayPal account | 1. Select PayPal 2. Login to PayPal 3. Confirm | PayPal credentials | Redirected to PayPal, payment processed | PayPal payment works | Pass | High
TC-065 | Payment | UPI Payment | Verify UPI payment works | UPI ID available | 1. Select UPI 2. Enter UPI ID 3. Approve on app | UPI ID: test@upi | Payment request sent, order confirmed on approval | UPI payment works | Pass | High
TC-066 | Payment | Payment Failure Handling | Verify payment failure handled gracefully | Simulated failure | 1. Use decline test card 2. Click Pay | Decline card: 4000000000000002 | Error: Payment declined, retry option shown | Failure handled correctly | Pass | Critical
TC-067 | Payment | Double Payment Prevention | Verify accidental double payment prevented | Payment in progress | 1. Click Pay 2. Click Pay again quickly | Valid card | Pay button disabled after first click | Double payment prevented | Fail | Critical | Bug: BUG-003 - double charge possible
TC-068 | Order | Order Confirmation Page | Verify order confirmation shows correct info | Order placed | 1. Complete checkout 2. Check confirmation page | Complete order | Order ID, items, total, ETA shown | Confirmation page correct | Pass | Critical
TC-069 | Order | Order Confirmation Email | Verify confirmation email received | Order placed | 1. Place order 2. Check email | User email | Email with order details received within 5 mins | Email received | Pass | High
TC-070 | Coupon | Coupon at Checkout | Verify coupon applied at checkout | Valid coupon | 1. Enter coupon at checkout 2. Apply | Coupon: FIRST50 | Discount applied to total | Coupon works at checkout | Pass | Medium
TC-071 | Tax | Tax Calculation | Verify tax calculated correctly based on location | Address with tax zone | 1. Enter address 2. Check tax amount | Address: New York | Correct state tax applied to order | Tax calculation correct | Pass | High
TC-072 | Order | Order Summary Review | Verify order summary before payment | Cart with items | 1. Reach payment step 2. Review order summary | Order with items | All items, quantities, prices, and total shown | Summary accurate | Pass | High
TC-073 | Payment | CVV Validation | Verify CVV validation | Checkout page | 1. Enter wrong CVV 2. Click Pay | CVV: 12 | Error: Invalid CVV | CVV validation works | Pass | Critical
TC-074 | Checkout | Back Navigation in Checkout | Verify data preserved on back navigation | Mid-checkout | 1. Fill address 2. Go to shipping 3. Click Back | Address data | Address data preserved on back | Back navigation keeps data | Pass | Medium
TC-075 | Payment | Net Banking Payment | Verify net banking payment | Bank account available | 1. Select Net Banking 2. Choose bank 3. Complete | Bank credentials | Redirected to bank, payment processed | Net banking works | Pass | Medium

## Security Testing
E-COMMERCE WEBSITE - TEST CASES ¦ Security Testing
TC ID | Module | Test Scenario | Test Case Description | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Priority | Remarks
TC-076 | Security | HTTPS Enforcement | Verify site forces HTTPS | None | 1. Access via HTTP 2. Check redirect | http://site.com | Auto redirected to HTTPS | HTTPS redirect works | Pass | Critical
TC-077 | Security | SQL Injection - Login | Verify SQL injection blocked on login | None | 1. Enter: ' OR '1'='1' in email | SQL injection string | Login rejected, no unauthorized access | Attack blocked | Pass | Critical
TC-078 | Security | XSS in Search | Verify XSS in search field blocked | None | 1. Search: <script>alert(1)</script> | XSS payload | Input sanitized, no script executes | XSS blocked | Fail | Critical | Bug: BUG-004
TC-079 | Security | CSRF Protection | Verify CSRF token validated on forms | None | 1. Submit form without CSRF token | Forged request | Request rejected with 403 error | CSRF protection works | Pass | Critical
TC-080 | Security | Password Hashing | Verify passwords stored as hash | Access to DB (admin) | 1. Check DB for user password | DB access | Password shown as bcrypt hash, not plaintext | Password hashed | Pass | Critical
TC-081 | Security | Brute Force Protection | Verify brute force on login blocked | None | 1. Attempt 10 wrong logins rapidly | Wrong credentials | Account locked or CAPTCHA triggered | Brute force blocked | Pass | Critical
TC-082 | Security | Unauthorized Access | Verify protected pages require login | None | 1. Access /profile without login | Unauthenticated user | Redirected to login page | Auth check works | Pass | Critical
TC-083 | Security | Admin Access by User | Verify regular user cannot access admin | Regular user logged in | 1. Try to access /admin | Regular user session | 403 Forbidden or redirect to home | Access control works | Pass | Critical
TC-084 | Security | Session Hijacking Prevention | Verify session tokens are secure | Logged in user | 1. Check session token in cookies 2. Verify HttpOnly and Secure flags | Browser cookies | Session cookie has HttpOnly and Secure flags | Secure cookies set | Pass | Critical
TC-085 | Security | Sensitive Data in URL | Verify sensitive data not in URL | None | 1. Navigate through checkout 2. Monitor URLs | Payment page | No card/personal data in URL parameters | Data not exposed in URL | Pass | Critical
TC-086 | Security | File Upload Validation | Verify file upload restricted to images | Profile page with photo upload | 1. Try uploading .exe file | Malicious file | Error: Only images allowed | File type validated | Pass | High
TC-087 | Security | Rate Limiting | Verify API rate limiting | None | 1. Make 100 API requests in 1 minute | API requests | 429 Too Many Requests returned | Rate limiting works | Pass | High

## Order Management
E-COMMERCE WEBSITE - TEST CASES ¦ Order Management
TC ID | Module | Test Scenario | Test Case Description | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Priority | Remarks
TC-088 | Orders | View Order History | Verify user can view past orders | Orders exist | 1. Go to My Orders | User with orders | All past orders listed with details | Order history shown | Pass | High
TC-089 | Orders | Order Detail View | Verify order details page | Order exists | 1. Click on an order | Order ID | Full order details: items, addresses, payment, status | Details shown correctly | Pass | High
TC-090 | Orders | Order Tracking | Verify order tracking works | Shipped order | 1. Click "Track Order" | Shipped order | Tracking page with status and ETA shown | Tracking works | Pass | High
TC-091 | Orders | Cancel Order | Verify order can be cancelled before shipping | Processing order | 1. Go to order 2. Click Cancel | Processing order | Order cancelled, refund initiated | Cancellation works | Pass | Critical
TC-092 | Orders | Cancel Shipped Order | Verify shipped order cannot be cancelled | Shipped order | 1. Try to cancel shipped order | Shipped order | Cancel button disabled or error shown | Cannot cancel shipped order | Pass | High
TC-093 | Returns | Return Request | Verify return request can be submitted | Delivered order | 1. Click Return 2. Select reason 3. Submit | Delivered order | Return request created, instructions sent | Return request works | Pass | High
TC-094 | Returns | Refund Processing | Verify refund processed after return | Return approved | 1. Check refund status | Approved return | Refund reflected in original payment method | Refund processed | Pass | Critical
TC-095 | Orders | Reorder | Verify reorder from previous order | Past order exists | 1. Go to past order 2. Click Reorder | Past order | Items added to cart for reordering | Reorder works | Pass | Medium
TC-096 | Orders | Invoice Download | Verify invoice PDF downloadable | Completed order | 1. Go to order 2. Click Download Invoice | Completed order | PDF invoice downloaded with correct details | Invoice downloads | Pass | Medium
TC-097 | Orders | Order Status Filter | Verify orders can be filtered by status | Multiple orders | 1. Select filter: "Delivered" | Mixed status orders | Only delivered orders shown | Status filter works | Pass | Medium
TC-098 | Orders | Order Search | Verify order search by order ID | Multiple orders | 1. Enter order ID in search | Valid order ID | Matching order found and displayed | Order search works | Pass | Medium
TC-099 | Returns | Return Window Expiry | Verify return not allowed after return window | Order beyond return window | 1. Try to return old order | Order > 30 days old | Error: Return window expired | Return window enforced | Pass | High
TC-100 | Orders | Email on Status Change | Verify emails sent on order status updates | Order placed | 1. Admin changes status 2. Check email | Order status change | Customer gets email for each status change | Status emails sent | Pass | High
TC-101 | Orders | Partial Order Cancellation | Verify individual items can be cancelled | Multi-item order | 1. Cancel one item from order | Multi-item order | Single item cancelled, rest proceed | Partial cancel works | Fail | Medium | Bug: BUG-005 - cancels all items

## Review
E-COMMERCE WEBSITE - TEST CASES ¦ Reviews & Ratings
TC ID | Module | Test Scenario | Test Case Description | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Priority | Remarks
TC-102 | Reviews | Add Review | Verify user can add product review | Purchased product, logged in | 1. Open product 2. Click Write Review 3. Add rating + text 4. Submit | Rating: 4, Review: Great product! | Review saved and visible on product page | Review posted successfully | Pass | High
TC-103 | Reviews | Review Without Purchase | Verify non-buyer cannot review | Not purchased product | 1. Open product 2. Try to add review | Non-purchased product | Error: Only verified buyers can review | Non-buyer blocked | Pass | High
TC-104 | Reviews | Edit Own Review | Verify user can edit their review | Own review exists | 1. Go to review 2. Click Edit 3. Update 4. Save | Updated review text | Review updated with edited text | Edit works | Pass | Medium
TC-105 | Reviews | Delete Own Review | Verify user can delete their review | Own review exists | 1. Click Delete on review | Own review | Review deleted from product page | Delete works | Pass | Medium
TC-106 | Reviews | Star Rating Display | Verify average rating calculated correctly | Multiple reviews | 1. Add reviews with different ratings 2. Check average | Ratings: 5,4,3 | Average shows 4.0 stars correctly | Average calculated correctly | Pass | High
TC-107 | Reviews | Image Upload in Review | Verify images can be uploaded with review | Verified purchase, logged in | 1. Write review 2. Upload product photo 3. Submit | Review image (JPG) | Image uploaded and shown with review | Image upload works | Pass | Medium
TC-108 | Reviews | Helpful Vote | Verify helpful/unhelpful vote on reviews | Reviews exist | 1. Click "Helpful" on a review | Any review | Vote count increases | Voting works | Pass | Low
TC-109 | Reviews | Report Review | Verify abusive review can be reported | Reviews exist | 1. Click "Report" on review 2. Select reason 3. Submit | Abusive review | Report submitted, review flagged | Report works | Pass | Medium
TC-110 | Reviews | Profanity Filter | Verify profanity filtered from reviews | None | 1. Submit review with profanity | Review with bad words | Review rejected or words censored | Profanity filtered | Pass | High

## Admin Panel
E-COMMERCE WEBSITE - TEST CASES ¦ Admin Panel
TC ID | Module | Test Scenario | Test Case Description | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Priority | Remarks
TC-111 | Admin | Admin Login | Verify admin can login to admin panel | Admin account | 1. Go to /admin 2. Enter admin credentials | Admin credentials | Admin logged in and dashboard shown | Admin login works | Pass | Critical
TC-112 | Admin | Add Product | Verify admin can add new product | Admin logged in | 1. Go to Products 2. Click Add New 3. Fill details 4. Save | Product data | Product saved and visible on site | Product added | Pass | Critical
TC-113 | Admin | Edit Product | Verify admin can edit existing product | Product exists | 1. Click Edit on product 2. Update price 3. Save | Updated price | Price updated on site | Edit product works | Pass | Critical
TC-114 | Admin | Delete Product | Verify admin can delete product | Product exists | 1. Click Delete on product 2. Confirm | Existing product | Product removed from site | Delete works | Pass | High
TC-115 | Admin | Update Order Status | Verify admin can update order status | Order exists | 1. Open order 2. Change status to Shipped 3. Save | Processing order | Status updated, customer notified | Status update works | Pass | Critical
TC-116 | Admin | Manage Users | Verify admin can view and manage users | Users exist | 1. Go to Users 2. View user list 3. Edit user role | User list | Users displayed, role can be changed | User management works | Pass | High
TC-117 | Admin | Disable User Account | Verify admin can disable user account | Active user | 1. Select user 2. Click Disable | Active user | Account disabled, user cannot login | Account disable works | Pass | High
TC-118 | Admin | Add Category | Verify admin can add product category | Admin logged in | 1. Go to Categories 2. Add new category 3. Save | Category: "Accessories" | Category appears in navigation | Category added | Pass | High
TC-119 | Admin | Coupon Management | Verify admin can create coupon codes | Admin logged in | 1. Go to Coupons 2. Create new coupon 3. Set discount 20% 4. Save | Coupon: SAVE20 | Coupon created and usable on checkout | Coupon creation works | Pass | High
TC-120 | Admin | Sales Report | Verify admin can generate sales report | Orders exist | 1. Go to Reports 2. Select date range 3. Generate | Date: last 30 days | Report with sales data generated | Report generates correctly | Pass | High
TC-121 | Admin | Inventory Management | Verify admin can update stock | Product in stock | 1. Open product 2. Update stock quantity 3. Save | Stock: 50 | Stock updated, site reflects new quantity | Inventory update works | Pass | High
TC-122 | Admin | Manage Reviews | Verify admin can moderate reviews | Reviews exist | 1. Go to Reviews 2. Approve or delete review | Pending review | Review status updated accordingly | Review moderation works | Pass | Medium
TC-123 | Admin | Banner Management | Verify admin can manage homepage banners | Admin logged in | 1. Go to Banners 2. Upload new banner 3. Save | Banner image | New banner displays on homepage | Banner management works | Pass | Medium
TC-124 | Admin | Admin Audit Log | Verify admin actions are logged | Multiple admin actions done | 1. Go to Audit Log | Admin actions | All admin actions logged with timestamp and admin ID | Audit log works | Pass | High
TC-125 | Admin | Dashboard Analytics | Verify dashboard shows key metrics | Data exists | 1. Open admin dashboard | Admin dashboard | Sales, orders, users, revenue shown correctly | Dashboard analytics correct | Pass | Medium
TC-126 | Admin | Process Refund | Verify admin can process customer refund | Return request approved | 1. Open return request 2. Click Process Refund 3. Confirm | Approved return | Refund processed, customer notified | Refund processing works | Fail | Critical | Bug: BUG-006

## Bug Report
E-COMMERCE WEBSITE - BUG REPORT
Bug ID | Related TC | Module | Bug Title | Description | Steps to Reproduce | Expected | Actual | Severity | Priority | Status | Assigned To
BUG-001 | TC-016 | Registration | XSS Vulnerability in Name Field | Script tags are not sanitized in registration name field allowing XSS | 1. Go to Register 2. Enter <script>alert('xss')</script> in name 3. Submit | Input sanitized, no script executes | Script executes - alert popup appears | Critical | Critical | Open | Dev Team Lead
BUG-002 | TC-050 | Shopping Cart | Guest Cart Not Merged on Login | Items added to cart as guest are lost when user logs in instead of merging | 1. Add item to cart as guest 2. Login to account 3. Check cart | Guest cart items merged with user cart | Cart is empty after login | Major | High | In Progress | Backend Dev
BUG-003 | TC-067 | Payment | Double Payment Possible on Network Delay | Clicking Pay button multiple times on slow network causes multiple charges | 1. Go to payment 2. Simulate slow network 3. Click Pay multiple times quickly | Pay button disabled after first click | Multiple orders placed and charged | Critical | Critical | Open | Dev Team Lead
BUG-004 | TC-078 | Security | XSS in Search Field | Search field executes injected JavaScript | 1. In search bar enter: <script>alert('xss')</script> 2. Press Search | Input sanitized, no script executes | Alert popup executes | Critical | Critical | Open | Security Team
BUG-005 | TC-101 | Orders | Partial Cancel Cancels Entire Order | Cancelling one item from multi-item order cancels all items | 1. Place multi-item order 2. Go to order 3. Click cancel on one item | Only selected item cancelled | Entire order cancelled | Major | High | In Progress | Backend Dev
BUG-006 | TC-126 | Admin Panel | Admin Cannot Process Refund | Refund button returns 500 error when admin tries to process refund | 1. Login as admin 2. Go to approved return 3. Click Process Refund | Refund processed successfully | 500 Internal Server Error | Critical | Critical | Open | Backend Dev

## Test Summary
TEST EXECUTION SUMMARY REPORT
OVERALL EXECUTION METRICS
Total Test Cases | 145
Passed | 126
Failed | 12
Blocked | 3
Not Executed | 4
Pass Rate | 86.9%
Total Bugs Found | 6
Critical Bugs | 4
High Bugs | 2
TEST CONCLUSION & RECOMMENDATIONS
✅ 86.9% of test cases passed - System is mostly stable and ready for UAT
⚠️ 6 bugs identified: 4 Critical, 2 High - Critical bugs must be fixed before release
🔴 Critical: XSS vulnerabilities in Registration and Search must be patched immediately
🔴 Critical: Double payment bug poses serious financial risk - fix required before go-live
🟡 Guest cart merge issue affects user experience - recommend fixing in next sprint
🔵 Recommend regression testing after all critical bug fixes are deployed
📅 Estimated re-testing effort: 2-3 days after bug fixes are available